## ACME Sprint Planner & Tracker
Sprint Planning and Tracking
PROJECT TITLE |  | Kitchen Story Application
PROJECT MANAGER |  | Shreyash Pawar
COMPANY NAME |  | Simpli Learn
DATE |  | 6/21/2022
PLANNER & TRACKER
Sprint 1
Sprint 2
TASK | TASK | TASK | AMOUNT OF WORK IN HOURS |  |  | STORY | START | DUE | DURATION | STATUS | PCT OF TASK | WEEK 1 |  |  |  | WEEK 2
ID | NAME | OWNER | ESTIMATE | COMPLETED | REMAINING | POINTS | DATE | DATE |  |  | COMPLETE | M | T | W | T | F | S | S | M
| SPRINT #1 | Shreyash Pawar | 10 | 10 | 0 | 4 | 2022-06-13 | 2022-06-16 | 4 | Completed | 100%
1 | Analysis Finished | Shreyash Pawar | 1 | 1 | 0 |  | 2022-06-13 | 2022-06-13 | 1 | Completed | 100%
2 | JSON Server Backend | Shreyash Pawar | 3 | 3 | 0 |  | 2022-06-14 | 2022-06-14 | 1 | Completed | 100%
3 | App Home | Shreyash Pawar | 3 | 3 | 0 |  | 2022-06-15 | 2022-06-15 | 1 | Completed | 100%
4 | Admin - Add New Item | Shreyash Pawar | 3 | 3 | 0 |  | 2022-06-16 | 2022-06-16 | 1 | Completed | 100%
| SPRINT #2 | Shreyash Pawar | 10 | 10 | 0 | 4 | 2022-06-17 | 2022-06-20 | 4 | Completed | 100%
5 | Admin - All Food Items | Shreyash Pawar | 3 | 3 | 0 |  | 2022-06-17 | 2022-06-17 | 1 | Completed | 100%
6 | User - Search based on Category | Shreyash Pawar | 3 | 3 | 0 |  | 2022-06-18 | 2022-06-18 | 1 | Completed | 100%
7 | Auth Guards | Shreyash Pawar | 2 | 2 | 0 |  | 2022-06-19 | 2022-06-19 | 1 | Completed | 100%
8 | Documentation | Shreyash Pawar | 2 | 2 | 0 |  | 2022-06-20 | 2022-06-20 | 1 | Completed | 100%